## Template
Risk ID | Date Logged | Risk | Project Obj. Impacted | Probability of Event | Impact | Approach | Mitigation Plan | Owner | Due Date | Status

## Example
Risk ID | Date Logged | Risk | Project Obj. Impacted | Probability of Event | Impact | Approach | Mitigation Plan | Owner | Due Date | Status
1 | 9/9/20XX | A reporting tool is not available to report Stockell EDI transaction generation errors | UBHC - Patient Accounting | 100% at onset of initial testing and % will deminish as test results improve as testing progresses | High | This risk can be lessened by monitoring and improving the accuracy of patient and tranacrion data in InsightCS | Coordinate testing with Gaffey and Associates. Upload EDI transactions to their website for editing. Gaffey and Associates. has access to a software application that provides EDI transaction generation errors and they will provide error reporting to UBHC. | Crystal Robinson, UBHC, Margaret Bistrovich,Gaffey | 9/13/20XX | Closed

## Instructions
The risk management process is a systematic and proactive approach to taking control of projects and decreasing the uncertainties. The Project Manager(s) log the risk(s) in the Risk Log if using the manual approach. Risk are managed and resolved and tracked using the Risk Log.
You will need to collect and track the following types of information:
1. Risk ID - A sequential numbering system can be used to identify risks.
2. Date Logged - The date the Project Manager(s) officially logged the risk.
3. Risk – Briefly describe the risk.
4. Project Obj. (Object) Impacted - The component of the project impacted by the risk. This is a good place to include any potential benefits a risk might have on the project.
5. Probability of Event – A percent estimate / likelihood the risk will occur.
6. Impact – Quantification on the level the risk might impact the project (i.e.: high impact, medium, or low).
7. Approach - Explanation of how the risk can be avoided or how the team can lessen the probability or impact to the project.
8. Mitigation Plan – The plan for risk mitigation.
9. Owner – Every risk should have an owner assigned to monitor and control the risk. It does not have to be the Project Manager(s), it can be any team member that has direct visibility to the risk event.
10. Due Date – Expected date of mitigation.
11. Status – Mitigation action status.